# Journal-tier landscape — Paper 2 (clinical disconnectome in TBI)

Purpose: planning document for Paper 2 venue strategy. For each realistic or stretch venue, spells out the framing that lands the paper, the analyses required to defend it, and a section-by-section manuscript breakdown with figure and table lists.

As-of: 2026-09-17. Author: Phind Ndagijimana (with Claude planning assist). Related docs: publication_strategy.md · paper2_disconnectome_outcomes.md · ../lesion_aware.md · ../disconnectome.md

────────────────────────────────────────────────────────────

## TL;DR

Paper 2 has three viable target venues and one honest fallback:

NeuroImage — if the head-to-head vs LQT/BCB normative-atlas SDC produces a quantitative divergence figure with clinical consequence in TBI. Methods-lead framing.

Brain — if the full Griffis-2019 SC → FC → behavior chain lands cleanly on N ≥ 50 with a neuropsych battery. Biology-lead framing.

Human Brain Mapping — safe landing under either framing at lower N or novelty bar. Default.

NeuroImage: Clinical — TBI-focused imaging-clinical backup; publishable version of Paper 2 in almost any scenario short of pipeline collapse.

Nature main is not in play. Nature Communications is a stretch requiring an external replication cohort (which we don't have). Design the analysis to unlock either the methods-lead or biology-lead path, run both, then choose venue by which contribution is quantitatively stronger — but lock the analysis plan (contrasts, primary metrics, benchmarks) before opening group results.

────────────────────────────────────────────────────────────

## Full venue landscape

| Venue | Realistic? | Framing that lands it | What we'd need to deliver | What we don't yet have |
| --- | --- | --- | --- | --- |
| Nature (main) | ❌ Not in play | Paradigm-shifting biology + broad reach beyond TBI | N > 500, multi-cohort replication, cross-disease generalizability | Everything |
| Nature Neuroscience | ❌ Stretch of stretch | Broad neuroscience insight beyond stroke/TBI | Very large N or exceptional mechanistic depth | Cohort scale, replication |
| Nature Communications | ⚠️ Stretch, conceivable | Full SC→FC→behavior + methods novelty + external replication | N ≥ 80 complete; independent replication cohort; crisp methods-vs-normative figure with clinical consequence | Replication cohort; N confirmation |
| Nature Human Behaviour | ⚠️ Stretch | Behavior-forward, domain-specific network mapping | Multi-domain neuropsych factor scores + clean domain-network mapping | Neuropsych battery confirmation |
| Brain | ✅ Realistic | Biology-lead: clinical-mechanistic story | N ≥ 50 complete cases + neuropsych + clean SC→FC coupling + incremental validity vs lesion volume | Clean cohort delivery |
| NeuroImage | ✅ Realistic | Methods-lead: patient-specific vs normative-atlas SDC head-to-head | Quantitative divergence figure vs LQT/BCB with downstream consequence (FC or behavior prediction) | The head-to-head analysis run |
| NeuroImage: Clinical | ✅ Very realistic | TBI-focused imaging-clinical | Standard clinical-imaging deliverables | Solid backup — no gap |
| Medical Image Analysis | ⚠️ Fit-dependent | Pipeline/engineering lead | Would require rewriting away from Griffis story | Different framing |
| Human Brain Mapping | ✅ Default landing | Either framing at lower N/novelty bar | Coherent whole; LeAPP was here | Nothing extra |
| Journal of Neurotrauma | ✅ Realistic backup | Clinical outcomes in TBI | GOSE + covariates on N ≥ 40; less demand on methods novelty | Nothing extra beyond baseline analysis |
| Cell Reports (Griffis's venue) | ❌ Not open | — | — | They published Griffis; won't accept extension |

How to read the table: ✅ means we can plausibly get there with the data we have or expect to have. ⚠️ means the venue is conceivable but only if specific additional deliverables land. ❌ means the venue is either editorially closed to us or requires resources (cohort scale, replication) we do not have.

────────────────────────────────────────────────────────────

## Path-determination logic

Three empirical questions with unknown answers today determine which venue is open:

| Question | If yes → | If no → |
| --- | --- | --- |
| Do patient-specific and normative-atlas SDC diverge meaningfully in TBI? | NeuroImage path viable | HBM (methods becomes supplement) |
| Is the SC→FC coupling reproducible cohort-wide? | Brain path viable | HBM |
| Do we have neuropsych battery + N ≥ 50 complete cases? | Brain path stronger | HBM |

Strategic rule: design the analysis to unlock either path; run both; then choose venue by which contribution is quantitatively stronger. Do not commit to a venue before results — but do lock the analysis plan (contrasts, primary metrics, benchmarks) before opening group results.

────────────────────────────────────────────────────────────

# Venue deep dives

## 1. NeuroImage — methods-lead (realistic primary target)

### Editorial identity

Reader base: neuroimaging methodologists, tool developers, computational imaging labs.

Reviewers reward: methods innovation with quantitative validation, head-to-head comparisons against standard tools (LQT, BCBtoolkit), sensitivity/robustness across parameters, reproducibility (containers, open code, provenance).

Reviewers reject on: biology-only stories without a methods contribution; qualitative rather than quantitative claims; missing benchmarks; single-atlas or single-method analyses; unclear why anyone should adopt the method.

Our fit: patient-specific lesion-aware SDC (from our lesion-aware ACT pipeline) vs normative-atlas SDC (LQT / BCBtoolkit) in TBI is a proper head-to-head. Our provenance JSON + Snakemake DAG + container distribution + open-code repo directly satisfy reproducibility expectations.

### Framing

Working title: Patient-specific lesion-aware disconnectomes in traumatic brain injury: a head-to-head comparison with normative-atlas approaches and consequences for network-level outcome prediction.

One-sentence claim: In TBI, patient-specific lesion-aware structural disconnection matrices diverge systematically from normative-atlas disconnection maps, and the divergence carries clinical signal that improves prediction of functional-connectivity disruption and behavior beyond normative-atlas SDC alone.

Abstract shape (~250 words):

│  Background. Structural disconnection (SDC) has emerged as a key mediator between focal brain lesions and network-level dysfunction. Existing SDC pipelines (LQT, BCBtoolkit) overlay lesion masks on normative white-matter atlases (HCP-842), avoiding patient-specific tractography but assuming that individual anatomy conforms to a healthy template.

│

│  Question. In traumatic brain injury — where mass effect, oedema, and bilateral injury deform individual anatomy — does patient-specific lesion-aware tractography produce different SDC estimates than normative-atlas overlay, and does the difference matter for downstream network and behavioral prediction?

│

│  Methods. On N=[cohort] TrackTBI subjects with clinician-traced lesion masks, we computed SDC using (1) our patient-specific lesion-aware pipeline (MRtrix 5ttedit -path, iFOD2 + SIFT2, DKT parcellation) and (2) two normative-atlas tools (LQT, BCBtoolkit). We compared SDC maps voxel- and edge-wise, and evaluated each SDC representation's ability to predict resting-state functional connectivity disruption and 6-month GOSE.

│

│  Results. Patient-specific SDC diverged from normative-atlas SDC in [X]% of subjects at edge magnitudes exceeding [Y]. Divergence was largest in subjects with [feature]. Patient-specific SDC predicted FC disruption with cross-validated R² of [Z], vs LQT [Z1]; and GOSE with AUC [W], vs LQT [W1]. Divergence and improvement in prediction were correlated at [ρ].

│

│  Interpretation. Normative-atlas SDC underestimates or misroutes disconnection in TBI. Patient-specific lesion-aware tractography, previously considered too fragile in lesioned brains, is now feasible and produces clinically meaningful improvements.

### Analysis required

Complete our factorial pipeline on the Paper 2 subset with the fixed arm (neurolit-lesion default; consider vbt-lesion as sensitivity).

Run LQT on the same subjects — install the MATLAB toolkit, normalize lesion masks to MNI (already done by pipeline for other purposes), export parcel-to-parcel SDC matrices.

Run BCBtoolkit on the same subjects — install, produce voxel-level disconnection probability maps and (optionally) Tractotron tract-level output.

Edge-wise comparison: correlate patient-specific SDC and LQT SDC matrices per subject. Report distribution of correlations, cases with r < 0.5, and identify subject-level features (lesion volume, lesion location, mass-effect severity) predicting divergence.

Voxel-wise comparison: overlay BCB disconnection probability maps with our patient-specific tract-level disconnection scores, report spatial concordance.

Downstream test 1: predict resting-state FC abnormality from each SDC representation using CCA or ridge regression, cross-validated across subjects, permutation-tested for significance.

Downstream test 2: predict 6-month GOSE from each SDC representation, controlling for lesion volume + age + sex + GCS.

Robustness: reproduce with alternative parcellation (Schaefer 200) and alternative fixed arm (vbt-lesion).

Reproducibility supplement: container digests, provenance JSON schema, code repo tag.

### Manuscript breakdown

Title. As above.

Abstract. ~250 words as sketched.

Introduction (~1000 words).

Widespread network dysfunction after focal lesions — Griffis et al. 2019 for stroke.

SDC as a mediator between lesion and network dysfunction.

Normative-atlas approaches (LQT, BCBtoolkit) are the current standard — reasons they became dominant (scalable, no patient DWI needed).

Limits in TBI specifically: heterogeneous mass effect, oedema, bilateral injury, midline shift; individual anatomy departs from normative template.

Our contribution: patient-specific lesion-aware tractography via 5ttedit -path, feasibility in TBI, head-to-head with normative-atlas tools, clinical downstream test.

Predictions: SDC divergence larger in high-mass-effect / bilateral subjects; patient-specific SDC improves FC and behavior prediction.

Methods (~2500 words).

Cohort: TrackTBI subject subset (N, inclusion criteria, lesion mask provenance).

Imaging: acquisition parameters (T1w, DWI shell b=[value], rs-fMRI TR/TE, sessions).

Preprocessing: QSIPrep pipeline, session/fmap handling, lesion mask registration.

Patient-specific SDC: FastSurfer recon, 5ttedit -path with lesion mask, iFOD2 tractography, SIFT2 weighting, DKT parcellation, disconnection matrix construction (spared-connectome options A/B/C).

Normative SDC: LQT (Griffis 2021), BCBtoolkit (Foulon 2018) — versions, parameter choices, MNI normalization procedure.

FC processing: fMRIPrep + XCP-D or equivalent, atlas-parcel time series, connectivity matrix.

Clinical outcomes: GOSE at 6 months, covariates (age, sex, education, GCS, lesion volume).

Statistical models: edge-wise correlation, CCA for SDC↔FC, ridge regression with cross-validation, permutation testing.

Software / reproducibility: containers, DAG, provenance JSON, code and container URLs.

Results (~2000 words).

Cohort characteristics table.

Figure 1: pipeline schematic (patient-specific vs normative).

Figure 2: representative subject — lesion + patient-specific SDC + LQT SDC + BCB disconnection map side by side.

Figure 3: cohort-wide SDC concordance distribution (violin plot per method-pair); scatter of concordance vs lesion volume / mass-effect metric.

Figure 4: FC prediction — cross-validated R² per SDC representation, per network.

Figure 5: GOSE prediction — ROC / AUC per SDC representation, with lesion-volume-only baseline.

Table 1: SDC divergence stratified by lesion location (frontal / temporal / parietal / occipital / bilateral).

Table 2: incremental-validity model comparison (nested model AIC/BIC).

Discussion (~1500 words).

Interpretation of divergence: where and why patient-specific SDC differs.

Clinical implications: which patient subgroups benefit most from patient-specific processing.

Comparison to Griffis 2019 (stroke): expect smaller divergence there — testable prediction.

Limitations: single-cohort, single-site, N constrained by lesion-mask + rs-fMRI + GOSE overlap.

Future directions: replication cohort, expansion to Deep Atropos 5TT, synthetic-MRI extension for CT-only subjects.

Data and code availability. BIDS derivatives on [repo], containers on GHCR + DockerHub, code on GitHub at tagged release.

Supplement (~2000 words).

S1: fMRI preprocessing details (fMRIPrep version, XCP-D pipeline, motion QC).

S2: LQT and BCBtoolkit parameter tables.

S3: Alternative-parcellation robustness (Schaefer 200).

S4: Alternative fixed-arm robustness (vbt-lesion).

S5: Provenance JSON schema example.

S6: Container digest table + reproducibility instructions.

Figures: 5 main + 6 supplement. Tables: 2 main + 3 supplement.

### Effort estimate

| Item | Effort |
| --- | --- |
| Complete cohort processing (fixed arm) | 2 weeks compute + 1 week QC |
| LQT install + run on all subjects | 2 weeks |
| BCBtoolkit install + run on all subjects | 2 weeks |
| fMRI preprocessing arm (fMRIPrep + XCP-D) | 3 weeks build + 2 weeks compute |
| SDC divergence analysis | 2 weeks |
| CCA / ridge regression modeling | 3 weeks |
| Manuscript drafting | 4 weeks |
| Supplement + code release | 2 weeks |
| Total (calendar time with overlap) | ~4 months |

### Risk / failure modes

Divergence is small — patient-specific and normative SDC agree within noise → methods contribution collapses; fall back to biology-lead (Brain / HBM) or supplement.

LQT MATLAB dependency — MATLAB-only install may be a barrier; may need to port to Python or use a container.

BCBtoolkit installation friction — historically MATLAB + FSL wrapper; Python components newer.

fMRI arm not yet in pipeline — real engineering to build.

Reviewer demand for replication cohort — NeuroImage may accept without one; expect at least a request for stronger justification if we don't have it.

────────────────────────────────────────────────────────────

## 2. Brain — biology-lead (realistic primary target)

### Editorial identity

Reader base: clinical neurologists, translational cognitive neuroscientists in clinical departments.

Reviewers reward: biological/mechanistic story with clinical implications, symptom-anatomy-mechanism triads, prognostic value, cohort-level generalizability, novel clinical insights.

Reviewers reject on: pure methods papers, no clinical interpretation, case reports, unclear biology, weak clinical justification.

Our fit: SC → FC → behavior chain in TBI (defined patient population, ~2M/year US, real clinical decision-support relevance); the Griffis 2019 stroke → TBI extension is a documented empty niche.

### Framing

Working title: Structural disconnection mediates functional network dysfunction and predicts cognitive recovery after traumatic brain injury.

One-sentence claim: Lesion-aware structural disconnection in TBI mechanistically explains resting-state functional connectivity disruption and predicts domain-specific cognitive outcome at 6 months, beyond what lesion volume or location alone can explain.

Abstract shape (~250 words):

│  Background. Focal traumatic brain injury (TBI) produces cognitive and functional deficits that often exceed what would be expected from local damage alone. In stroke, structural disconnection of white-matter tracts has been shown to mechanistically explain widespread functional network dysfunction (Griffis et al. 2019). Whether the same mechanism generalizes to TBI — where lesions are morphologically more heterogeneous — is unknown.

│

│  Methods. We processed N=[cohort] TrackTBI subjects with clinician-traced lesion masks through a lesion-aware structural connectome pipeline that inserts individual lesion masks into MRtrix's pathology channel during tractography. We computed patient-specific structural disconnection matrices, resting-state functional connectivity, and correlated both with 6-month Glasgow Outcome Scale-Extended (GOSE) and multi-domain neuropsychological composites (processing speed, executive function, memory, language).

│

│  Results. Structural disconnection was spatially concordant with functional connectivity disruption (canonical correlation r = [X], p < 0.001) across all subjects. Disconnection scores in domain-specific networks predicted domain-specific cognitive deficits (attention → dorsal attention network SDC; memory → medial temporal SDC; executive → fronto-parietal SDC). Structural disconnection improved 6-month GOSE prediction over a lesion-volume + demographics baseline (ΔAUC = [Y], cross-validated).

│

│  Interpretation. In TBI, focal lesions produce widespread network dysfunction via structural disconnection of long-range tracts. Disconnection-based biomarkers offer clinically actionable prognostic value that lesion volume alone does not capture. These findings extend the Griffis 2019 disconnection framework from stroke to TBI and support incorporating tract-level disconnection into TBI recovery models.

### Analysis required

Complete cohort processing on fixed arm (neurolit-lesion default).

rs-fMRI processing (fMRIPrep + XCP-D) → FC matrices.

FC abnormality per subject vs a healthy-control normative distribution (borrow CIDUR controls, ~26 with rs-fMRI if available; else public HCP normative distribution).

CCA analysis: SDC ↔ FC-abnormality — replicate Griffis 2019 method.

Domain-specific network → cognitive-composite regressions (Schaefer/Yeo parcellation + neuropsych factor scores).

GOSE ordinal regression with lesion-volume baseline vs SDC-augmented model; cross-validated ΔAUC + permutation testing.

Face-validity figure: group-average disconnectome in MNI, lesion topology overlay.

Subgroup analysis: does the mechanism generalize across lesion locations / severities / mechanisms of injury?

### Manuscript breakdown

Title. As above.

Abstract. ~250 words as sketched.

Introduction (~1200 words).

Widespread post-TBI network dysfunction — brief clinical framing (2M/year, chronic sequelae).

Griffis 2019 stroke framework — SC → FC → behavior — and why TBI is a natural next test case.

Existing TBI network work (Palacios, Kuceyeski, Warren) and its limits.

Our contribution: first cohort-scale disconnection-based mechanism paper in TBI with prospective SC → FC → behavior model.

Predictions.

Methods (~2500 words).

Cohort: TrackTBI subject subset — inclusion / exclusion / demographics / clinical severity distribution.

Imaging: T1w, DWI, rs-fMRI acquisition + preprocessing (references cite Palacios 2022 for TRACK-TBI protocol).

Structural disconnection: lesion-aware pipeline (brief; cite our methods paper for full).

Functional connectivity: fMRIPrep + XCP-D + parcellation + connectivity matrix construction.

Clinical outcomes: GOSE assessment (window, assessor training), neuropsych battery.

Statistical models: CCA (SDC ↔ FC), ridge regression, ordinal regression for GOSE.

Missing data handling.

Results (~2000 words).

Cohort characteristics table.

Figure 1: group-average disconnectome in MNI space (face validity).

Figure 2: CCA — first component's SDC loadings + FC loadings + scatter of subject scores.

Figure 3: domain-specific network → cognitive-composite scatter plots (5 panels: attention, memory, executive, language, motor).

Figure 4: GOSE prediction — ROC curves for lesion-volume baseline vs SDC-augmented vs SDC+FC-augmented models.

Figure 5: representative-subject case series (3 subjects: mild, moderate, severe) — lesion + SDC + FC-abnormality + outcome.

Table 1: cohort demographics and clinical severity.

Table 2: incremental-validity model comparison (nested models, cross-validated AUC, permutation p).

Table 3: domain-network mapping (which network's SDC predicts which composite).

Discussion (~1800 words).

Mechanism: SDC → FC → behavior generalizes from stroke to TBI.

Domain-specific network mapping strengthens biological interpretability.

Clinical implications: disconnection-based biomarker for prognosis; potential for targeted rehab.

Comparison to Griffis 2019: similarities and differences in stroke vs TBI (magnitude of effect, network specificity).

Limitations: single-cohort, single-site, N constrained, no independent replication, self-report symptom vs objective outcome.

Future directions: longitudinal recovery trajectories, intervention targets.

Data and code availability.

Supplement (~2000 words).

S1: rs-fMRI preprocessing details and motion QC.

S2: Neuropsych battery details, factor analysis, missing-data handling.

S3: Alternative parcellation / atlas robustness.

S4: Alternative fixed arm robustness (vbt-lesion).

S5: SDC method-choice sensitivity (patient-specific vs LQT — this is where the "methods-lead" would live if we split it out; if kept as biology paper, this is a brief robustness check).

S6: Subgroup analyses by injury mechanism, lesion location.

Figures: 5 main + 5 supplement. Tables: 3 main + 2 supplement.

### Effort estimate

| Item | Effort |
| --- | --- |
| Complete cohort processing (fixed arm) | 2 weeks compute + 1 week QC |
| fMRI preprocessing arm (fMRIPrep + XCP-D) | 3 weeks build + 2 weeks compute |
| Neuropsych factor analysis / composite construction | 2 weeks (assumes data available) |
| CCA + regression modeling | 3 weeks |
| Manuscript drafting | 4 weeks |
| Clinical reviewer / neurologist coauthor rounds | 2 weeks |
| Total (calendar time with overlap) | ~4 months |

### Risk / failure modes

SC → FC coupling is noisy or weak — CCA doesn't yield a coherent first component → biology story collapses; fall back to HBM or methods-lead.

Neuropsych battery is thin — reviewers demand multi-domain factor scores; if we only have GOSE + RPQ the paper's domain-specificity story shrinks and Brain becomes harder.

Single-site / single-cohort — Brain reviewers may ask for external replication; likely a resubmission gate.

GOSE prediction incremental effect is small — if ΔAUC is < 0.05 above lesion volume, incremental-validity claim is unpersuasive.

────────────────────────────────────────────────────────────

## 3. Human Brain Mapping (HBM) — default landing

### Editorial identity

Reader base: broad — imaging labs, clinical, translational, methods researchers. LeAPP (Bey et al. 2024) was here, so our methodological family is welcome.

Reviewers reward: solid neuroscience with imaging methods; connectivity/network analyses; N = 40–100 with honest interpretation; well-executed studies at moderate scale.

Reviewers reject on: incoherent whole; unclear contribution; missing basic reproducibility; unjustified methodological choices.

Our fit: either the methods-lead or biology-lead framing works at HBM under lower bar. If neither the head-to-head divergence figure nor the SC→FC coupling is exceptional, HBM is the honest home.

### Framing

Working title (methods-lead flavor): Lesion-aware structural disconnectomes in traumatic brain injury: methods and clinical correlates. Working title (biology-lead flavor): Structural disconnection and outcome after traumatic brain injury: a lesion-aware disconnectome study.

Both frames use the same data and analyses; HBM welcomes either as long as the story is coherent and well-defended.

### Analysis required

Same as NeuroImage or Brain versions, with these relaxations acceptable at HBM:

N < 50 acceptable if biology is coherent

Single-atlas SDC analysis acceptable (no LQT/BCB head-to-head required if we frame it as biology-lead)

Single-outcome (GOSE) acceptable if we frame the paper honestly as prognostic rather than domain-specific

Cohort-only (no external replication) is fine

### Manuscript breakdown

Follows either NeuroImage or Brain outline depending on which frame we lead with, but:

Introduction shorter (~800 words) — HBM permits less exhaustive positioning

Methods the same rigor

Results — 4 main figures instead of 5, 2 main tables instead of 3

Discussion shorter (~1200 words), fewer speculation paragraphs

Supplement less exhaustive

### Effort estimate

Approximately 80% of the NeuroImage or Brain effort — the analytic backbone is the same, but writing and supplement effort is lighter.

### Risk / failure modes

Truly weak results everywhere — even HBM will reject an incoherent submission. HBM's rejection risk is not "your ceiling is too low" but "the story doesn't hang together."

────────────────────────────────────────────────────────────

## 4. NeuroImage: Clinical — solid backup

### Editorial identity

Reader base: clinical neuroimaging researchers, translational imaging labs.

Reviewers reward: clinically-relevant imaging findings with methodological transparency, TBI-focused work, prognostic biomarkers.

Reviewers reject on: methodological weaknesses, unclear clinical relevance, non-clinical framing.

Our fit: natural home for a Paper 2 that emphasizes clinical/prognostic relevance without needing the full Brain-tier biological mechanism story.

### Framing

Working title: Lesion-aware structural disconnectomes as a prognostic biomarker in traumatic brain injury.

Framing is prognostic-clinical: does SDC predict outcome? Do specific disconnection patterns map to specific deficits? Less demand on mechanism than Brain.

### Analysis required

Cohort processing (fixed arm)

GOSE prediction with SDC + lesion volume baseline

Optional: domain-specific mapping if neuropsych available

Simpler statistical framework acceptable (logistic regression + AUC)

### Manuscript breakdown

Shorter than Brain/NI (typical NI:Clinical papers are ~4000 words main text)

4 main figures, 2 tables

Focused supplement

### Effort estimate

Roughly 70% of Brain effort.

### Risk / failure modes

Unclear clinical relevance — if the outcome prediction improvement is small in absolute terms, reviewers may question clinical utility.

────────────────────────────────────────────────────────────

## 5. Nature Communications — stretch, conceivable

### Editorial identity

Reader base: broad multidisciplinary — neuroscientists, imaging, clinical, computational biology.

Reviewers reward: paradigm-advancing findings, methodological novelty PLUS strong biology, cross-cohort or cross-domain validation, broad reach.

Reviewers reject on: single-cohort findings, narrow methodological contributions, results that fit better at a specialty venue.

Our fit: only if we can deliver both the methods head-to-head AND the full biology chain AND some form of external validation.

### Framing

Working title: Patient-specific lesion-aware disconnectomes reveal mechanism and prognosis of network dysfunction after traumatic brain injury.

Combined framing: methods + biology + clinical prognostic value + (ideally) replication.

### Analysis required (in addition to NeuroImage + Brain analyses)

External replication cohort — a second TBI cohort with lesion masks + DWI + rs-fMRI + outcomes. We don't have this. Would require establishing a collaboration.

OR: LQT/BCB benchmarking on synthetic lesions in healthy controls (CIDUR N=26) as a form of methodological replication.

OR: cross-domain validation showing our patient-specific SDC generalizes to another disease population (stroke) where Griffis is the gold standard.

Larger cohort (N ≥ 80 complete cases) — depends on TrackTBI cohort availability.

### Manuscript breakdown

Fusion of NeuroImage and Brain outlines

6 main figures, 3 tables

Substantial supplement

### Effort estimate

Roughly 2× NeuroImage or Brain effort due to replication cohort establishment.

### Risk / failure modes

Cannot get replication cohort — reviewers will likely reject or bounce to specialty venue.

Result complexity outstrips a Nature Comm-length manuscript — trying to fit both methods and biology into 4000 words is hard.

────────────────────────────────────────────────────────────

## 6. Nature Human Behaviour — stretch

### Editorial identity

Reader base: cognitive neuroscientists, behavioral scientists.

Reviewers reward: behavior-forward findings, domain-specific network-behavior mapping, novel behavioral biomarkers.

Reviewers reject on: methods-forward papers, weak behavioral characterization.

Our fit: only if TRACK-TBI neuropsych battery is comprehensive (multiple domains) AND network-domain mapping is exceptionally clean.

### Framing

Working title: Domain-specific network disconnection predicts cognitive recovery after traumatic brain injury.

### Analysis required

Multi-domain neuropsych factor scores (Corbetta-style battery, requires TRACK-TBI export to be rich)

Network-native parcellation (Schaefer / Yeo mapped onto neuropsych domains)

Clean domain-network mapping with hold-out validation

Domain-specific incremental validity

### Manuscript breakdown

Similar to Brain but with behavior-heavy framing and less imaging methodology.

### Effort estimate

Similar to Brain if neuropsych battery is available; substantially more if we need to construct composite scores.

### Risk / failure modes

Neuropsych battery not sufficiently multi-domain — story collapses.

Domain-specific mapping is noisy — the paper's central claim fails.

────────────────────────────────────────────────────────────

## 7. Medical Image Analysis — fit-dependent

### Editorial identity

Reader base: medical imaging engineers, computational imaging researchers.

Reviewers reward: engineering/pipeline innovation, quantitative methods contributions, benchmarking.

Reviewers reject on: clinical-narrative framing, weak engineering novelty.

Our fit: would require completely rewriting away from the biology story, leading instead with the lesion-aware ACT pipeline as an engineering contribution.

### Framing

Working title: A reproducible pipeline for patient-specific lesion-aware structural connectomics in focal brain lesions.

### Analysis required

Pipeline benchmarking (runtime, reproducibility, failure modes, resource requirements)

Methods head-to-head vs LQT/BCB with engineering-flavored metrics

Container / provenance / DAG documentation as a first-class contribution

### Manuscript breakdown

Engineering-heavy. Main figures show pipeline DAG, benchmark tables, container digests.

### Effort estimate

Would compete with Paper 1 (factorial paper) for the engineering framing. Probably not worth pursuing as a separate paper unless Paper 1 pivots.

### Risk / failure modes

Overlaps with Paper 1 — probably better to fold engineering framing into Paper 1 supplement.

────────────────────────────────────────────────────────────

## 8. Journal of Neurotrauma — realistic clinical backup

### Editorial identity

Reader base: TBI-focused clinical and translational researchers.

Reviewers reward: TBI-specific findings, prognostic biomarkers, clinical relevance.

Reviewers reject on: non-TBI content, weak clinical rationale.

Our fit: natural home if we want to lead purely with clinical prognostic value.

### Framing

Working title: Structural disconnectome as an outcome biomarker after traumatic brain injury.

### Analysis required

Basic: cohort processing, GOSE prediction, lesion volume baseline. Neuropsych optional, rs-fMRI optional.

### Manuscript breakdown

Shorter than Brain; focus on clinical relevance.

### Effort estimate

Roughly 60% of Brain effort.

### Risk / failure modes

Clinical utility unclear at cohort N — reviewers ask for larger validation.

────────────────────────────────────────────────────────────

# Strategic path selection

## Design the analysis to unlock either path

Regardless of which venue is the eventual target, the following analyses are required and should be built in parallel:

Complete cohort processing with fixed lesion-aware arm — required for any Paper 2 version

fMRI preprocessing arm in the pipeline — required for biology-lead (Brain / HBM biology)

LQT + BCB installation and cohort run — required for methods-lead (NeuroImage)

Complete-case clinical spreadsheet — required for any Paper 2 version

Schaefer / 4S parcellation — required for network-native analyses (Brain domain-specific)

Neuropsych factor analysis (if battery available) — required for Brain domain-specific + Nature Human Behaviour

## When to commit to a venue

After analyses 1–5 are complete and quality-assessed — not before.

Lock analysis plan before opening group-level results — pre-register internally.

Choose venue based on which contribution is quantitatively stronger — head-to-head divergence vs SC→FC coupling.

## Pre-registration principles

Before opening group results:

[ ] Primary imaging arm fixed (default neurolit-lesion)

[ ] Primary clinical outcome fixed (default 6-month GOSE)

[ ] Primary imaging outcome fixed (default global disconnection score)

[ ] Visit-timing rule fixed (default 2wk imaging → 6mo outcome)

[ ] Covariate set fixed (age, sex, education, GCS, lesion volume)

[ ] Network-to-domain mapping fixed (which atlas → which composite)

[ ] Incremental-validity benchmark models specified

[ ] Complete-case N threshold specified (proceed at N ≥ 45, limitations at 30–44, fold into Paper 1 at < 30)

────────────────────────────────────────────────────────────

# Master timeline

Assuming clinical export arrives within 2 months and cohort processing runs in parallel:

| Month | Milestone |
| --- | --- |
| Month 1 | Clinical data-dictionary request; cohort processing (fixed arm) start; fMRI arm engineering start |
| Month 2 | Complete-case spreadsheet built; N confirmed; analysis plan locked; LQT/BCB install |
| Month 3 | Cohort processing complete; fMRI arm complete on cohort; SDC head-to-head figures drafted |
| Month 4 | SC→FC coupling analysis complete; GOSE / neuropsych regression complete |
| Month 5 | Venue decision (NeuroImage vs Brain vs HBM); manuscript drafting begins |
| Month 6 | First draft complete; internal coauthor review |
| Month 7 | Coauthor revisions; final polish |
| Month 8 | Submission |

Realistic revision + resubmission adds 2–4 additional months to publication.

────────────────────────────────────────────────────────────

# Appendix A — Analysis inventory (what needs building)

[ ] fMRI preprocessing arm (fMRIPrep + XCP-D or equivalent) — new pipeline component

[ ] LQT installation + wrapper (MATLAB or Python port) — new tool

[ ] BCBtoolkit installation + wrapper — new tool

[ ] Schaefer 200 / 4S parcellation runs on the Paper 2 subset — existing pipeline supports, just add config

[ ] SDC divergence analysis script (edge-wise, subject-level, subgroup) — new analysis code

[ ] CCA implementation for SDC↔FC — new analysis code

[ ] Incremental-validity nested regression suite — new analysis code

[ ] MNI group-average disconnectome — new analysis code

[ ] Complete-case spreadsheet builder — new analysis code

[ ] Face-validity figure generator — new analysis code

# Appendix B — Reproducibility inventory (what's already built)

[x] Containerized pipeline (dkt_connectome, dkt_lesion_act, dkt_vbt SIFs on GHCR + DockerHub)

[x] Snakemake DAG with per-step marker files

[x] Provenance JSON at each step (lesion_aware_act.json, disconnectome.json, etc.)

[x] Per-arm output isolation (RESULTS_ROOT/arms/<arm>/)

[x] BIDS App interface

[x] QC dashboards (subject-level HTML)

[x] Disconnectome integrity QC (Options A/B/C sensitivity)

[x] Six-arm factorial experiment tree on pilot subject

# Appendix C — Manuscript checklists

## NeuroImage checklist

[ ] Methods innovation stated crisply in abstract

[ ] Head-to-head figure (patient-specific vs LQT vs BCB) as Figure 1 or 2

[ ] Quantitative divergence metrics reported

[ ] Clinical downstream validation as Results, not Discussion

[ ] Reproducibility statement + container digests

[ ] Code and container URLs in data availability

[ ] Robustness analyses in supplement

## Brain checklist

[ ] Clinical relevance stated in first paragraph

[ ] Griffis 2019 explicitly cited and positioned

[ ] SC → FC → behavior chain figure as Figure 2 or 3

[ ] Domain-specific mapping figure

[ ] Incremental validity vs lesion volume table

[ ] Group-average disconnectome face-validity figure

[ ] Cohort demographics table

[ ] Clinical implications discussion

## HBM checklist

[ ] Either NeuroImage or Brain checklist, minus 1–2 items

[ ] Honest limitations section

[ ] Coherent whole (methods + biology + clinical)

## Appendix D — What TRACK-TBI clinical export should include

Request from PI / data core:

| Variable | Rationale |
| --- | --- |
| GOSE at each visit (2wk, 3mo, 6mo, 12mo) + visit date | Primary outcome |
| RPQ or PCL-5 at each visit | Secondary symptom outcome |
| Neuropsych battery (Trail Making A/B, WAIS Processing Speed, CVLT-II, BVMT-R, COWA, SDMT) with visit dates | Domain-specific outcomes (unlocks Brain + NHB) |
| GCS (field + admission) | Injury severity covariate |
| PTA, LOC duration | Injury severity covariate |
| Age at injury, sex, education years, race, prior TBI history | Mandatory covariates |
| Mechanism of injury (MVA / fall / assault / sports / other) | Descriptive + subgroup stratification |
| Lesion characteristics (volume mm³, lobar location) — if not already in BIDS derivatives | Mandatory covariate |
| Site / scanner | Harmonization covariate |
| Enrollment date + inclusion/exclusion metadata | Cohort construction |

Ask specifically: "For subjects with lesion masks + DWI + rs-fMRI in the TrackTBI-Sub subset, what fraction have (a) 6-month GOSE, (b) a neuropsych composite at 6 months, and (c) all covariates listed above?"

────────────────────────────────────────────────────────────

## See also

publication_strategy.md — cross-paper strategy

paper2_disconnectome_outcomes.md — Paper 2 planning stub (analysis registry, complete-case template)

../lesion_aware.md — lesion-aware ACT methodology

../disconnectome.md — Step 4.1 methods

../validation.md — validation cohort context

../references.md — full bibliography