# Paper 2B — readiness checklist

As-of: 2026-10-07

Related: index.md · ../disconnectome/disconnectome_missing.md

## Snapshot

| Category | Ready | Partial | Missing |
| --- | --- | --- | --- |
| Patient-specific SDC pipeline | ✅ |  |  |
| fMRI Arm B (dual stream) | ✅ | ⚠️ DKT BOLD fallback |  |
| 7-subject pilot | ✅ |  |  |
| Analysis scripts (`analysis/paper2b/`) | ✅ |  |  |
| **LQT batch** |  |  | ❌ |
| BCB (optional) |  |  | ❌ |
| Imaging cohort N ≥ 40 |  |  | ❌ |
| Analysis plan sign-off |  | ⚠️ |  |
| Manuscript draft |  |  | ❌ |

No external clinical export required for 2B primary analyses.

## Must have before submission

### Imaging & comparators

[ ] LQT installed and run per imaging complete-case subject

[ ] LQT → DKT-78 alignment documented (same node order as patient-specific)

[ ] Cohort N ≥ locked threshold in analysis_plan.md §8

[ ] Primary SC↔FC metric locked (§6.2)

[ ] BOLD provenance table in supplement (XCP-D T1w denoised vs fallback)

### Analysis

[ ] analysis_plan.md signed

[ ] run_paper2b_analysis.sh run on full imaging cohort

[ ] imaging_cohort_tracker.md filled

### Manuscript

[ ] manuscript_skeleton.md drafted

[ ] Figures 1–5 per skeleton

[ ] Code + container availability statement

## Pilot done (2026-10-07)

[x] 7 × 2WK neurolit DWI disconnectome

[x] 7 × 2WK fMRI Arm B (xcp + fmristroke)

[x] Exploratory coupling (run_pilot_fc_analysis.sh → can mirror under analysis/paper2b/)

## Risks

| Risk | Mitigation |
| --- | --- |
| LQT ≈ patient-specific everywhere | Publish negative methods; subset where they differ |
| SC↔FC weak at edge level | Emphasize RQ1; frame RQ3 as exploratory until N grows |
| Overlap with Paper 2 | 2B = no outcomes; Paper 2 adds GOSE as separate sign-off |